## Slide 1: CSSE3113 – Introduction to Software Engineering Software Project Scheduling

## Slide 2: Eight Reasons for Late Software Delivery
An unrealistic deadline established by someone outside the software engineering group and forced on managers and practitioners within the group
Changing customer requirements that are not reflected in schedule changes
An honest underestimate of the amount of effort and /or the number of resources that will be required to do the job
Predictable and/or unpredictable risks that were not considered when the project commenced

## Slide 3: Eight Reasons for Late Software Delivery
Technical difficulties that could not have been foreseen in advance
Human difficulties that could not have been foreseen in advance
Miscommunication among project staff that results in delays
A failure by project management to recognize that the project is falling behind schedule and a lack of action to correct the problem

## Slide 4: Basic Principles for Project Scheduling
Compartmentalization
  The project must be compartmentalized into a number of manageable activities, actions, and tasks; both the product and the process are decomposed
Interdependency
  The interdependency of each compartmentalized activity, action, or task must be determined
  Some tasks must occur in sequence while others can occur in parallel
  Some actions or activities cannot commence until the work product produced by another is available
Time allocation
  Each task to be scheduled must be allocated some number of work units
  In addition, each task must be assigned a start date and a completion date that are a function of the interdependencies
  Start and stop dates are also established based on whether work will be conducted on a full-time or part-time basis

## Slide 5: Basic Principles for Project Scheduling
Effort validation
  Every project has a defined number of people on the team
  As time allocation occurs, the project manager must ensure that no more than the allocated number of people have been scheduled at any given time
Defined responsibilities
  Every task that is scheduled should be assigned to a specific team member
Defined outcomes
  Every task that is scheduled should have a defined outcome for software projects such as a work product or part of a work product
  Work products are often combined in deliverables
Defined milestones
  Every task or group of tasks should be associated with a project milestone
  A milestone is accomplished when one or more work products has been reviewed for quality and has been approved

## Slide 6: Relationship Between People and Effort
Common management myth:
If we fall behind schedule, we can always add more programmers and catch up later in the project
  This practice actually has a disruptive effect and causes the schedule to slip even further
  The added people must learn the system
  The people who teach them are the same people who were earlier doing the work
  During teaching, no work is being accomplished
  Lines of communication (and the inherent delays) increase for each new person added

## Slide 7: 40-20-40 Distribution of Effort
A recommended distribution of effort across the software process is 40% (analysis and design), 20% (coding), and 40% (testing)‏
Work expended on project planning rarely accounts for more than 2 - 3% of the total effort
Requirements analysis may comprise 10 - 25%
  Effort spent on prototyping and project complexity may increase this
Software design normally needs 20 – 25%
Coding should need only 15 - 20% based on the effort applied to software design
Testing and subsequent debugging can account for 30 - 40%
  Safety or security-related software requires more time for testing

## Slide 8: 40-20-40 Distribution of Effort
Testing
Coding
Design
Analysis
P
6/1
6/4
6/23
7/14
8/2
9/5
40
20
40
Example: 100-day project

## Slide 9: Task Network

## Slide 10: Defining a Task Set
A task set is the work breakdown structure for the project
No single task set is appropriate for all projects and process models
  It varies depending on the project type and the degree of rigor (based on influential factors) with which the team plans to work
The task set should provide enough discipline to achieve high software quality
  But it must not burden the project team with unnecessary work
  An example is given in next two slides.

## Slide 13: Purpose of a Task Network
Also called an activity network
It is a graphic representation of the task flow for a project
It depicts task length, sequence, concurrency, and dependency
Points out inter-task dependencies to help the manager ensure continuous progress toward project completion
The critical path
  A single path leading from start to finish in a task network
  It contains the sequence of tasks that must be completed on schedule if the project as a whole is to be completed on schedule
  It also determines the minimum duration of the project

## Slide 15: Example Task Network
Task A
3
Task B
3
Task E
8
Task F
2
Task H
5
Task C
7
Task D
5
Task I
4
Task M
0
Task N
2
Task G
3
Task J
5
Task K
3
Task L
10
Where is the critical path and what tasks are on it?

## Slide 16: Example Task Network with Critical Path Marked
Task A
3
Task B
3
Task E
8
Task F
2
Task H
5
Task C
7
Task D
5
Task I
4
Task M
0
Task N
2
Task G
3
Task J
5
Task K
3
Task L
10
Critical path: A-B-C-E-K-L-M-N

## Slide 17: Determining the Critical Path for Project X

## Slide 18: Timeline Chart

## Slide 19: Mechanics of a Timeline Chart
Also called a Gantt chart; invented by Henry Gantt, industrial engineer, 1917
All project tasks are listed in the far left column
The next few columns may list the following for each task:
  projected start date
  projected stop date
  projected duration
  actual start date
  actual stop date
  actual duration
  task inter-dependencies (i.e., predecessors)‏

## Slide 20: Mechanics of a Timeline Chart
1
None
Pred.
3/1
3/1
0
Milestone N
2
2/28
1/1
2 months
Task A
1
Finish
Start
Duration
Task Name
Task #
Jan Feb Mar Apr May Jun Jul Aug Sep Oct
To the far right are columns representing dates on a calendar
The length of a horizontal bar on the calendar indicates the duration of the task
When multiple bars occur at the same time interval on the calendar, this implies task concurrency
A diamond in the calendar area of a specific task indicates that the task is a milestone; a milestone has a time duration of zero